## Slide 1
StorNext 5 Test Cycle Review
Ted Pogue
January 17, 2014

## Slide 2
Notes: We are making the presentation sessions available to a small group of team members via WebEx.
The main purpose of the presentations is to record the sessions for future use.
If you are attending a WebEx session, please keep your questions relevant to the purpose of the meeting, support of MySQL in SN 4.3.
If you do have questions and feedback about things outside the main focus you can either send them by email or give them to the presenters outside the class.

## Slide 3: Overview
Review of coverage, criteria, and results
Hit the highlights, not a comprehensive review
Focus on file system and platform testing
Overall test results positive

## Slide 4: DVT Entrance and Exit Criteria
DVT1 Entrance criteria
  Relaxed to meet the 12/13 test complete date
  Allowed development to complete necessary work while simultaneously starting DVT1 QA efforts
  Slow ramp of resources
DVT1 Exit Criteria
  The following DVT1 exit criteria was not met due to the slow initial ramp of resources and some key bug fixes that required significant retest.
  95% Test execution – 74% achieved
  80% Tests Passing - ~90% passing
DVT2 Entrance Criteria
  DVT2 entrance criteria were relaxed to continue driving towards the release date
  DVT1 exit criteria was only partially met
  Critical test blocker bugs resolved by development – 2 remained open
DVT2 Exit Criteria
  DVT2 exit criteria were met
  99% Test execution
  95% Tests Passing

## Slide 5: Final DVT Exit (Release) Criteria
Final DVT exit criteria were partially met (4 criticals deferred)
Successful completion of Maturity test
All QA bugs verified
4 critical bugs were deferred based on management decision
  Bug 45763 - Storage Manager Component f.685:1:sdisk1 : A Checksum error has occurred
    Turned out to be an issue with old FC HBA Firmware
  Bug 45715 - Data corruption was seen on LAN client running Vdbench
    Very difficult to hit replication/deduplication issue
    Duplicate of 4.3.3 filed Bug 46191- snpolicy retrieval race can cause client to read zeros in file
    Problem present since 4.0.0. Hasn’t been customer reported to date.
    Resolved in 5.0.1
  Bug 46089 - PANIC: /usr/cvfs/bin/fsm "bt_merge_and_free failed" file sn/snfs/fsm/alloc_btree.c, line 835
    Only saw this once and have been unable to reproduce since.
  Bug 46108 - PANIC: /usr/cvfs/bin/fsm ASSERT failed "ext.idiext_frblock >= next_frblock" file
    This is not a regression
    Seen when running FSX test
    Issue is overlapping extents (frblocks)
    cvfsck resolves the issue in SN5
    Resolved in 5.0.1

## Slide 6: Deferred Testing
Some testing was deferred to SN 5.0.1 to meet schedule
  Windows MDC
  Some Xsan testing
    Windows MDC with Xsan client
    Xsan MDC with FX client
  MAS Agent
  Lattus
    Timing of Lattus 3.3.1 release
    Completed Lattus-X/Lattus-M on 1/9/14

## Slide 7: Configurations
Scalability
  Gigafiles – 1+ billion managed files
  Sagan – New for SN 5 – 5 billion unmanaged files
Performance, includes SSD
Fragmentation
Storage Manager
Sntest Automation
Platform
VMware

## Slide 8: OS Coverage
Each tester used a mix in their testing
Tested install/upgrade – SN 4.3.2, 4.3.3, 4.7, 4.7.0.1, 5
Tested with back rev clients
Extensive testing with multipathd
Saw minimal OS specific issues
  Linux
    SLES 11, RHEL5, RHEL6, Centos5, Centos6
    MDC and client
    Various service packs
    SNTest covers Linux only currently
  Windows
    7, 2008, 8, 2012R1
    Windows MDC some testing, not full regression
  Platform
    M660, M662, M440, M330, G301, G301
    Performed by SN QA and Platform QA teams
    M662 commonly used as MDC for various clients
  Xsan
    Tested as client to Linux MDC
    Umami, 3.0, 2.3, 2.2
  Unix – Solaris 10 & 11, HPUX, AIX

## Slide 9: Platform Test Upgrade Matrix

## Slide 10: SNTest Automation Code Coverage
SNTest has two types of code coverage which overlap
  Development integration code coverage – minimum set of tests
    Run against all branch checkins
    Does not cover GUI
    Function coverage increased from 28% (SN 4.7) to 49% (SN 5).
    Condition/Decision coverage increased from 22% (SN 4.7) to 28% (SN 5).
  DVT Automation code coverage
    Automation was run weekly
    Does not cover GUI
    Cumulatively executed 1457 test suites, 1296 test suites passed, 5953 machine hours were used and 42 regression bugs were generated
    Function coverage increased from 49% (SN 4.3.3) to 59% (SN 5).
    Condition/Decision coverage increased from 29% (SN4.3.3) to SN 5 38% (SN 5).
  Definitions
    Function coverage – subroutine function entered
    Condition/Decision – if, then, else, etc.

## Slide 11: Platform Test Results
DVT Results
  Total Tests Executed – 221
  Pass 220
  Fail 1
  All high priority bugs resolved
Stability Maturity Results
  Maturity test started 11/25/13 and ended on 12/13/13
  The M662R system was installed with SN 4.7 and i/o run for 3 days then upgraded to the latest SN 5

## Slide 12: File System Test Highlights
Created ~588 new tests, including:
  Metadata Upgrade
    Didn’t observe performance hit during conversion
    SNtest performed many conversions with customer metadata
    Tested upgrades with ACLs, quotas, xattrs, affinities, corrupt fs, fault injection during conversion, small inode
  4K blocksize - Data integrity after conversion, many starting block sizes
  Creation and restore of metadump
  Cvfsck – recovery after fault injection
  Journaling – replay and resizing
  New Buffer Cache
  Btree
  New Allocator – File system aging, stripe alignment
  Affinities – auto affinities, affinity preference
  Fragmentation – Vidio, file system space test
New File System specific tests
  fslt - file system load test
  fslst - file system ls test
  fsfst - file system file synchronization (consistency) test

## Slide 13: Other Test Highlights
Replication/Deduplication
  HA environment
  Replication with TSM Policy as source and target
  New blockpool 3.8 was tested
  Back-rev source and target were tested (SN 4.3.3 and 4.7)
  Upgrade from SN 4.3.3 and 4.7 to SN 5 tested
  Replication with 30M files and 2M directories
  Part of Maturity Test
Memory usage
  Noticed increased overall memory usage
  Profiling/quantifying memory usage changes in SN 5.0.1 versus 4.7
Fragmentation
  Overall looked good
  Still working allocator changes in SN 5.0.1 for specific cases
  Snfsdefrag struggles to do its work in nearly full FS cases

## Slide 14: Scalability
Action | Definition | SN 4.3.3 Result | SN 5 Result
Carl Sagan |  |  | 
File creation | files/second | N/A | 6400
Metadump rebuild | elapsed hh:mm | N/A | 35:53
Restore from metadump | elapsed hh:mm | N/A | 88:54
cvfsck | elapsed hh:mm | N/A | 6:40
Gigafiles |  |  | 
TSM rebuild policy | elapsed hh:mm | 17:15 | 13:05
Full snbackup | elapsed hh:mm | 135:52 | 12:45
Partial snbackup | elapsed hh:mm | 88:38 | 5:51
Clean versions | elapsed hh:mm | 3:00 | 3:32
cvfsck | elapsed hh:mm | 76:05 | 4:42
Metadump rebuild | elapsed hh:mm | 8:58 | 27+ hours*
Upgrade metadata | elapsed hh:mm | N/A | 92:23
Upgrade MySQL schema | elapsed hh:mm | N/A | 35:33
File creation | files/second | 800 | 1400
Store to sdisk | files/second | 274 | 300
Size of metadump | bytes | 1.235 trillion | 476+ billion
* SN 5 rebuild occurs in the background without downtime as in SN 4.x

## Slide 15: Maturity Test
The primary goal of the Maturity Test is to monitor performance of the product within a complex system configuration over time and under a continuous load that would be representative of a customer workflow. The product is monitored for memory usage, data integrity, disk and resource consumption, and fragmentation while the systems are populated with test data.
The StorNext 5 Maturity Test bed was run informally for the entirety of DVT2 with weekly updates to the latest interim build.
The StorNext 5 Maturity Test was formally started on 11/25/2013 with RC1 build 39009.
The Test met its goal on 12/9 of 5 days contiguous and 10 days total running time with 3 days of reset for upgrades. At that time, failovers under load were successfully performed as specified in the Test Plan. The test continued until 12/16 when the Lattus WAS storage system was taken down for upgrade.
Total file ingest via Replication/Storage Manager: 2119950, via Windows: 228492

## Slide 16: Summary Metrics
*100% of non-deferred test cases were run. These percentages include deferred test cases.
SN5 Metrics Summary |  |  |  |  |  |  |  | 
Test Type | Percent Run | Percent Pass | Percent Fail | Total | Run | Pass | Fail | Defer
SNTest Automation | 100% | 98% | 2% | 173 | 173 | 169 | 4 | 0
StorTest Manual | 82%* | 98% | 2% | 1923 | 1568 | 1544 | 24 | 355
Platform | 100% | 99.5% | 0.5% | 221 | 221 | 220 | 1 | 0
Total | 85%* | 99% | 1% | 2317 | 1962 | 1933 | 29 | 355

## Slide 17: Defect Breakdown
Unsurprisingly, the majority of the bugs were in the core SNFS category.

## Slide 18: Summary
DVT entrance and exit criteria were relaxed in the interest of meeting the release
  First run testing continued through DVT2 and resulting bug discovery rates remained high until the end of DVT2
  Significant development help was required to complete all bug verifications prior to release.
Some non-critical areas of concern were deferred for further analysis to 5.0.1, including:
  Memory usage
  Fragmentation
4 critical bugs were deferred that were either not regressions or had an expected HW RCA
SN5 met final release criteria (except 4 critical bugs deferred) and some significant milestones
  98% pass rate overall of 1962 total test cases/suites run.
  The goals established in the PRD were generally met and verified
  Performance for backups showed significant improvement over SN 4.3.3
  Test was able to scale up to 5 Billion files per single MDC.
  Sntest automation code coverage increased significantly
    Function coverage increased from 49% to 59%.
    Condition/Decision coverage increased from 29% to 38%